# PayStream Reliability Lab: Product Lifecycle with Prototyping and Test Modules

Prototype, MVP, Final Working Product + Tests, Commercial-Ready Deployed Product

Stage 0: Prototype --> Stage 1: MVP --> Stage 2: Final Working Product + Tests --> Stage 3: Commercial-Ready
(throwaway spikes)    (end-to-end       (secure, observable, failure-tested,        (cloud-deployed, IaC, GitOps,
                       thin slice)       automated test suite)                       DR, SLOs, support, releases)

Indicative timeline for one person: Stage 0 overlaps week 1; Stage 1 weeks 1 to 2; Stage 2 weeks 3 to 5; Stage 3 weeks 6 to 9 (optional stretch). A stage starts only when the previous stage’s exit criteria are met.

# Stage 0: Prototyping Modules (throwaway, learning-oriented)

Purpose: answer specific technical questions cheaply before committing to a design. Prototype code is not carried into the product; learnings are recorded as ADRs.

| ID | Module | Question answered | Output |
| --- | --- | --- | --- |
| P0 | Environment check | Does the hardware handle 3 brokers + Schema Registry + monitoring? | Resource measurements, chosen heap sizes |
| P1 | Single-broker produce/consume | Basic producer/consumer behaviour with Spring Kafka | Working snippet, config notes |
| P2 | Avro + Schema Registry | Can we serialise/evolve schemas and see compatibility rejections? | Sample schemas, compatibility ADR |
| P3 | 3-node KRaft cluster | Quorum, leader election, partition placement | Compose file draft, ADR on topology |
| P4 | TLS and SASL spike | Cert generation, listeners, SCRAM users, ACL enforcement | Cert scripts draft, ADR on listener layout |
| P5 | Metrics spike | JMX exporter to Prometheus to Grafana; which metrics matter | Metric shortlist for alerts |
| P6 | Fault spike | What actually happens when one broker is stopped? | Notes feeding drill D1 design |

Prototype test approach. Manual verification plus short written observations. No coverage targets.

Exit criteria. Every module answered its question in writing; topology, listener layout and partition count ADRs exist.

# Stage 1: MVP

Scope. A thin, working end-to-end slice with minimal security and monitoring.

- 3-broker KRaft cluster and Schema Registry via Compose

- txn-producer, fraud-detector (amount rule only), notifier (Postgres write)

- Basic Grafana dashboard (broker up, URP, consumer lag)

- CI: build and unit tests

- make up brings the stack up; README quickstart

## Test modules at MVP

| ID | Module | Type | Examples |
| --- | --- | --- | --- |
| T1 | Unit tests | Automated | Fraud amount rule boundaries; serializer config; mapping logic |
| T2 | Smoke test | Automated script | Stack starts; topic created; one message flows producer to alert to DB |
| T3 | Single integration test | Testcontainers | Produce transaction above threshold, assert alert row exists |
| T4 | Manual broker-kill check | Manual | Stop one broker; confirm flow continues (precursor to D1) |

## Exit criteria (MVP gate)

- Cold start to working flow in one command, reproduced on a clean machine or VM.

- End-to-end flow works for 10 minutes at 100 msg/s with no errors.

- CI green.

- Known limitations listed (no security, one rule, no DLQ).

# Stage 2: Final Working Product + Tests

Scope. Everything in the Must and most Should items of the PRD.

- Security: mTLS, SASL/SCRAM, ACLs, cert rotation procedure

- Velocity rule with Kafka Streams; DLQ and retry topics; idempotent consumer

- Connect with Postgres CDC

- Full dashboards and alert rules

- Six drills with evidence, RCA and runbooks

- Rolling upgrade and broker expansion procedures, tested

- Topic/ACL/schema as code with CI validation and drift check

- Documentation set complete

## Test modules at Final

| ID | Module | Type | Tools | Representative cases |
| --- | --- | --- | --- | --- |
| T1 | Unit | Automated | JUnit, Mockito | Rule logic, DLQ routing decisions, idempotency branch logic |
| T5 | Streams topology | Automated | TopologyTestDriver | Velocity window edges: N-th transaction at 59.9 s vs 60.1 s; out-of-order events |
| T6 | Integration | Automated | Testcontainers | Duplicate delivery produces one effect; DLQ on malformed record; consumer restart resumes correctly |
| T7 | Contract / schema | Automated (CI) | Registry compatibility API | Adding a field with default passes; removing a field fails; type change fails |
| T8 | Security | Automated | Scripts, openssl s_client | Plaintext refused; wrong SCRAM password refused; expired cert refused; each service denied non-granted operations |
| T9 | Config lint | Automated (CI) | validate-config.py, yamllint | Naming standard, RF, min ISR, wildcard ACL detection |
| T10 | Performance | Scripted | perf-test tools, load generator | Throughput ceiling and p99 latency at 1k, 2.5k, 5k msg/s; record bottleneck |
| T11 | Chaos / drills | Scripted + evidence | chaos/*.sh | D1 to D6 as in PRD section 7; each run twice |
| T12 | Upgrade | Scripted | tests/upgrade | Rolling upgrade with continuous load; assert zero producer errors and bounded lag |
| T13 | Expansion | Scripted | Reassignment tools | Add broker, reassign partitions, verify balance and no data loss |
| T14 | Soak | Scripted | Load generator | 8 to 24 hours at moderate load; watch for memory, disk and lag drift |

## Test targets

- Line coverage on service modules at least 70%, with 90% or more on rule and idempotency logic.

- All Must-level functional requirements have at least one automated test; Should-level have at least one automated or scripted test.

- Every drill executed twice with consistent results; evidence stored in chaos/results/.

## Exit criteria (Final gate)

- 6 of 6 drills documented with RCA and runbook.

- Zero lost messages and zero duplicate sink effects in the D1 30-minute run.

- Rolling upgrade completed with zero producer errors.

- CI green on main including security and lint stages.

- Performance baseline published with hardware stated.

- A reviewer reproduces D1 from the docs alone.

# Stage 3: Commercial-Ready Deployed Product

“Commercial-ready” here means operable by a team other than its author, with deployment, recovery, cost and support defined. It does not mean certified, and it does not mean battle-tested by real traffic.

## Scope

| Area | Deliverable |
| --- | --- |
| Deployment | Kubernetes deployment (Helm or Confluent for Kubernetes) on a managed cloud cluster; dedicated controllers; anti-affinity and rack/zone awareness |
| IaC | Terraform for network, cluster, storage, DNS; no manual console changes |
| GitOps | Environment promotion dev to UAT to prod by pull request; approvals on prod; automated drift detection |
| Secrets and PKI | Vault or cloud secret manager; cert-manager automated rotation; no long-lived static credentials |
| DR | Second cluster with replication; documented and tested failover and failback; measured RTO/RPO |
| Backup | Config and schema backups; tested restore; documented data-retention stance |
| Reliability | SLOs defined (availability, end-to-end latency, durability), error budgets, alert routing to on-call |
| Security hardening | Network policies, pod security, image scanning gate, dependency scanning gate, audit logging of admin actions, threat model reviewed |
| Compliance mapping | Control mapping to a chosen framework as documentation (for example PCI-DSS-style controls); explicitly not a certification |
| Cost and capacity | Cost model per environment, capacity plan, scaling procedure |
| Release engineering | Semantic versioning, changelog, rollback procedure, upgrade-compatibility matrix |
| Support model | Severity definitions, escalation path, incident template, post-incident review template, on-call runbook index |
| Licensing | Written inventory of every component’s license and any commercial-feature dependency |
| Legal/ops docs | Limitations, support boundaries, data-handling statement |

## Test modules at Commercial-Ready

| ID | Module | Type | Representative cases |
| --- | --- | --- | --- |
| T15 | K8s parity | Automated | Same functional suite (T6, T8) passes on Kubernetes |
| T16 | Chaos on K8s | Chaos Mesh / Litmus | Pod kill, node drain, zone loss, network partition, storage latency |
| T17 | DR failover | Scripted + timed | Primary cluster down; fail over; measure RTO and RPO; fail back |
| T18 | Restore | Scripted | Restore config and schemas into a clean cluster; verify |
| T19 | Penetration / adversarial | Manual + scripted | Credential stuffing against SASL, ACL bypass attempts, cert misuse, webhook/CI abuse if CI-driven changes exist |
| T20 | Capacity and scale | Load | Find saturation point; verify scale-out procedure; validate cost model |
| T21 | Upgrade across versions | Scripted | N to N+1 rolling upgrade on K8s with load; rollback test |
| T22 | Game day | Team exercise | Unannounced fault injected; responder uses only runbooks; time to detect and recover measured |

## Exit criteria (Commercial-ready gate)

- Entire stack deployed from Git with no manual steps; destroy and recreate verified.

- DR failover and restore each executed successfully and timed.

- SLOs defined and observed for at least 2 weeks with alerts routed correctly.

- No critical or high unresolved findings from dependency, image and security tests.

- A person who did not write the system executes a runbook successfully during a game day.

- Licensing inventory complete; cost model reviewed.

- Documented limitations section is honest about what has and has not been proven.

# Stage Summary

| Stage | Purpose | Key evidence | Approx. effort |
| --- | --- | --- | --- |
| 0 Prototype | De-risk unknowns | ADRs, spike notes | Days |
| 1 MVP | Prove the end-to-end path | Working flow, smoke test | About 2 weeks |
| 2 Final + tests | Deliver the real value | 6 drills, runbooks, test suite, baseline | About 3 weeks |
| 3 Commercial-ready | Make it operable by others | Cloud deploy, DR, SLOs, game day | About 3 to 4 weeks (optional) |

# Definition of Done (applies to every work item)

- Code or config merged via pull request with CI green.

- Tests written at the appropriate level and passing.

- Config lint passes; no new high-severity scan findings.

- Documentation or runbook updated if behaviour or operations changed.

- Observability considered: metric, log or alert added where a new failure mode exists.

- Reproducible by make target or documented command.

# Risks to the Lifecycle Itself

- Skipping Stage 2 to reach Stage 3 produces a deployed system with no evidence it works. Do not do this.

- Treating drills as a one-time demo instead of repeatable tests lets them rot; keep them runnable in CI nightly where feasible.

- Stage 3 can absorb unlimited time. Time-box it, and cut to the minimum gate (K8s deploy, IaC, DR test, SLOs) if schedule slips.